## Sheet1
Code | Activities | Expected Outputs/Results | Indicators | Sources of Verification | Responsible structure | Partner structures | Physical Programming |  |  |  |  | Financial Programming (Thousands of CFA francs) |  |  |  |  | Total Cost (Thousands FCFA) | Funding (thousands of CFA francs)
[7 empty] | 2024 | 2025 | 2026 | 2027 | 2028 | 2024 | 2025 | 2026 | 2027 | 2028 |  | State | Partners | What to look for
Global Goal: Strengthen the resilience of people and ecosystems to climate change for inclusive and sustainable growth in Burkina Faso
Axis 1: STRENGTHENING THE ADAPTIVE CAPACITIES OF PRIORITY SECTORS
Specific Objective 1.1: SO 1.1. Strengthening the adaptation capacities of agro-pastoral sectors to CC
Expected Outcome 1.1.1: Farm resilience to the adverse effects of climate change is strengthened | [6 empty] | Financial Programming (Thousands of CFA francs) 2024: 5 359 000; Financial Programming (Thousands of CFA francs) 2025: 5 060 000; Financial Programming (Thousands of CFA francs) 2026: 5 180 000; Financial Programming (Thousands of CFA francs) 2027: 4 740 000; Financial Programming (Thousands of CFA francs) 2028: 4 740 000 | 23 349 000 | 0 | 23 349 000 | 0
Action 1.1.2.1:- Improving animal and fisheries health | [6 empty] | Financial Programming (Thousands of CFA francs) 2024: 1 325 000; Financial Programming (Thousands of CFA francs) 2025: 1 325 000; Financial Programming (Thousands of CFA francs) 2026: 1 325 000; Financial Programming (Thousands of CFA francs) 2027: 1 325 000; Financial Programming (Thousands of CFA francs) 2028: 1 325 000 | 6 625 000 | 0 | 6 625 000 | 0
Activity 1.1.2.1.1 | Systematically vaccinate and deworm animals | Animals are routinely vaccinated and dewormed | Number of animals vaccinated and dewormed | Commerce | DGSV; DRARAH; | PRAPS; PDPS; PRECEL | X | X | X | X | X | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 1 250 000 | 0 | 1 250 000 | 0
Activity 1.1.2.1.2 | Providing anti-stress heat medication for animals and fish | Heat-related stress to animals and fish is reduced | Amount of anti-stress medication provided | Commerce | DGSV; DRARAH. | PRAPS; PDPS; PRECEL | X | X | X | X | X | 75 000 | 75 000 | 75 000 | 75 000 | 75 000 | 375 000 | 0 | 375 000 | 0
Activity 1.1.2.1.3 | Keeping livestock in a fixed location to withstand heat waves and associated diseases | Cattle are sedentary | Number of sedentary herds | Commerce | DGPA; DGFORM; DRARAH | PRAPS; PDPS; PRECEL | X | X | X | X | X | 1 000 000 | 1 000 000 | 1 000 000 | 1 000 000 | 1 000 000 | 5 000 000 | 0 | 5 000 000 | 0
Action 1.1.2.2: Increase the productivity of animal and fisheries resources | [6 empty] | Financial Programming (Thousands of CFA francs) 2024: 3 619 000; Financial Programming (Thousands of CFA francs) 2025: 3 320 000; Financial Programming (Thousands of CFA francs) 2026: 3060000; Financial Programming (Thousands of CFA francs) 2027: 2620000; Financial Programming (Thousands of CFA francs) 2028: 2620000 | 15 239 000 | 0 | 15 239 000 | 0
Activity 1.1.2.2.1 | Building water collection points | Dependence on water in times of drought and extreme heat for the population and livestock is reduced | Number of water collection points constructed | Reception P.V.; Report | DGPA; ERDG | PRAPS; PDPS; PRECEL | Physical Programming 2025: X; Physical Programming 2026: X; Financial Programming (Thousands of CFA francs) 2024: 150 000; Financial Programming (Thousands of CFA francs) 2025: 150 000 | 300 000 | 0 | 300 000 | 0
Activity 1.1.2.2.2 | Carry out pastoral infrastructure and specific equipment (security, food and sanitation) in the pastoral areas transformed into ZIPA | Pastoral infrastructure and specific equipment are built | Number of infrastructures built Number of equipment built | Commerce; Reception P.V | DGPA; DGFORM; DRARAH | PRAPS; PDPS; PRECEL | X | X | X | X | X | 3 404 000 | 3 115 000 | 3 005 000 | 2 565 000 | 2 565 000 | 14 654 000 | 0 | 14 654 000 | 0
Activity 1.1.2.2.3 | Carry out artificial insemination activities of improved breeds adapted to the hot climate | Breeding females are inseminated with seeds of improved breeds adapted to the warm climate | Number of animals inseminated | Commerce | DGPA; CMAP; DRARAH | PRAPS; PDPS; PRECEL; PDEL-ZPO | X | X | X |  | X | 65000 | 55 000 | 55 000 | 55 000 | 55 000 | 285 000 |  | 285 000 | 0
Action 1.1.2.3: | Improving the availability and accessibility of animal feed | [5 empty] | Financial Programming (Thousands of CFA francs) 2024: 415 000; Financial Programming (Thousands of CFA francs) 2025: 415 000; Financial Programming (Thousands of CFA francs) 2026: 795 000; Financial Programming (Thousands of CFA francs) 2027: 795 000; Financial Programming (Thousands of CFA francs) 2028: 795 000 | 1 485 000 | 0 | 1 485 000 | 0
Activity 1.1.2.3.1 | Cultivate, mow and conserve natural fodder | The cultivation, mowing and conservation of natural fodder is practiced | Quantity of fodder stored in tonnes by livestock farmers | Commerce; Data Collection Sheets | DGPA; DRARAH | PRAPS; PDPS; PRECEL | X | X | X | X | X | 355 000 | 355 000 | 355 000 | 765 000 | 765 000 | 1 245 000 | 0 | 1 245 000 | 0
Activity 1.1.2.3.2 | Recovering degraded land and replenishing vegetation cover using ESC/DRS techniques | Degraded land is reclaimed and vegetation cover is replenished | Number of hectares of degraded land reclaimed | Commerce | DGPA; DGPV; DGFOMER | PRAPS; PDPS; PRECEL | X | X | X | X | X | 60 000 | 60 000 | 60 000 | 30 000 | 30 000 | 240 000 | 0 | 240 000 | 0
Expected outcome 1.1.2: Reduced vulnerability of agro-pastoralists, pastoral and fisheries resources to the adverse effects of climate change
Strategic Objective SO 1.2. Strengthen the adaptive capacity of the forestry, fisheries and wildlife sectors to CCs
Expected Outcome 1.2.1: The resilience of water resources to the adverse effects of climate change is strengthened | [6 empty] | Financial Programming (Thousands of CFA francs) 2024: 125 000; Financial Programming (Thousands of CFA francs) 2025: 85 000; Financial Programming (Thousands of CFA francs) 2026: 55 000; Financial Programming (Thousands of CFA francs) 2027: 55 000; Financial Programming (Thousands of CFA francs) 2028: 55 000 | 375 000 | 0 | 375 000 | 0
Action 1.2.1.1: Capacity building of producers on livestock and fisheries production techniques | [16 empty] | 375 000 | 0 | 375 000 | 0
Activity 1.2.1.1.1 | Training of producers on livestock and fisheries production techniques in the face of climate change | Producers are trained in animal and fisheries production techniques in the face of climate change | Number of producers trained in livestock and fisheries production techniques | Commerce; | DGPA; DGFOMER; DRARAH | PRAPS; PDPS; PRECEL | X | X | X | X | X | 125 000 | 85 000 | 55 000 | 55 000 | 55 000 | 375 000 | 0 | 375 000 | 0
Expected Outcome 1.2.2: The adaptive capacity of forest ecosystems, including wildlife, to the adverse effects of climate change is strengthened | [16 empty] | 1 984 650 | 34 700 | 0 | 1 949 580
Action 1.2.2.1: Improvement of drainage systems | [16 empty] | 1 949 700 | 120 | 0 | 1 949 580
Activity 1.2.2.1.1 | Rehabilitating Dams in Wildlife Protected Areas | Dams are rehabilitated in wildlife protected areas | Number of dams rehabilitated | PS-PASP | DGEF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.2.2.1.2 | Construct dams in wildlife protected areas | Dams are built in wildlife protected areas | Number of dams built | PS-PASP | DGEF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Activity 1.2.2.1.3 | Landscaping forest management sites | forest management sites are being developed | Area of forest management sites under management (ha) | PS-PASP | DGEF |  | 120 | 120 | 120 | 120 | 120 | 389940 | 389940 | 389940 | 389940 | 389940 | 1 949 700 | 120 | 0 | 1 949 580
Action 1.2.2.2: Improving the conservation and restoration of forest resources | [16 empty] | 34 445 | 34 445 | 0 | 0
Activity 1.2.2.2.1 | Producing Seedlings | seedlings are produced | Number of seedlings produced | PS-PASP | DGEF |  | Physical Programming 2024: 11; Physical Programming 2025: 11; Physical Programming 2026: 11; Physical Programming 2027: 11; Physical Programming 2028: 11 | 16 500 | 16500 | 0 | 0
Activity 1.2.2.2.2 | Planting Seedlings | Seedlings are planted | Number of seedlings produced | PS-PASP | DGEF |  | Physical Programming 2024: 10.5; Physical Programming 2025: 10.5; Physical Programming 2026: 10.5; Physical Programming 2027: 10.5; Physical Programming 2028: 10.5 | 15 677 | 15676,5 | 0 | 0
Activity 1.2.2.2.3 | Recovering degraded land from forest ecosystems | land is reclaimed | Area of forest ecosystems reclaimed | PS-PASP | DGEF |  | Physical Programming 2024: 5000; Physical Programming 2025: 5000; Physical Programming 2026: 5000; Physical Programming 2027: 5000; Physical Programming 2028: 5000 | 2 250 | 2250 | 0 | 0
Activity 1.2.2.2.4 | Organize information and awareness-raising sessions for stakeholders on SLM | information and awareness-raising sessions for stakeholders on SLM are organised | Number of actors sensitized | PS-PASP | DGEF |  | Physical Programming 2024: 100; Physical Programming 2025: 100; Physical Programming 2026: 100; Physical Programming 2027: 100; Physical Programming 2028: 100 | 18 | 18 | 0 | 0
Activity 1.2.2.2.5 | Supporting local authorities in the creation of conservation spaces | Local authorities are supported in the creation of conservation spaces | Number of communities supported | PS-PASP | DGEF |  | 25 | 25 | 25 | 25 | 25 | 250 | 250 | 250 | 250 | 25 | 1 250 | 0 | 0 | 1 250
Action 1.2.2.3: Promote improved forest seed varieties | [16 empty] | 505 | 135 | 0 | 0
Activity 1.2.2.3.1 | Producing improved forest seeds | Improved forest seeds are produced | Amount of seed produced (kg) | PS-PASP | DGEF |  | Physical Programming 2024: 500; Physical Programming 2025: 500; Physical Programming 2026: 500; Physical Programming 2027: 500; Physical Programming 2028: 500 | 250
Activity 1.2.2.3.2 | Disseminating Improved Forest Seeds | Improved forest seeds are disseminated | Quantity of seed released (kg) | PS-PASP | DGEF |  | Physical Programming 2024: 500; Physical Programming 2025: 500; Physical Programming 2026: 500; Physical Programming 2027: 500; Physical Programming 2028: 500 | 120
Activity 1.2.2.3.3 | Creating Nutritious Gardens | Nutritious gardens are created | Number of gardens created | PS-PASP | DGEF |  | 35 | 35 | 35 | 35 | 35 | 27 | 27 | 27 | 27 | 27 | 135 | 135 | 0 | 0
Action 1.2.2.4: Improved water conservation and availability in FPAs
Action 1.2.2.4: Development of early warning systems | [16 empty] | 0 | 0 | 0 | 0
Activity 1.2.2.4.1 | Support for the establishment of bushfire management committees
Activity 1.2.2.4.2 | Organize consultation meetings between stakeholders
Action 1.2.2.4: Improving the availability of climate and weather information
Specific objectives OS 1.3. Strengthening the adaptive capacity of the infrastructure, housing, energy and health sectors to the CC
Expected Outcome 1.3.1: The energy sector's adaptive capacity to the adverse effects of climate change is strengthened
Expected Outcome 1.3.2: The resilience of infrastructure and habitats to the effects of climate change is strengthened | [6 empty] | Financial Programming (Thousands of CFA francs) 2025: 38 145 270 610; Financial Programming (Thousands of CFA francs) 2026: 123 047 017 633; Financial Programming (Thousands of CFA francs) 2027: 158 139 751 911; Financial Programming (Thousands of CFA francs) 2028: 64563000778 | 211 206 225 274 | 211 206 225 198
Action 1.3.2.1: Development of the stormwater drainage system in cities | [6 empty] | Financial Programming (Thousands of CFA francs) 2025: 38 145 270 610; Financial Programming (Thousands of CFA francs) 2026: 123 047 017 633; Financial Programming (Thousands of CFA francs) 2027: 158 139 751 911; Financial Programming (Thousands of CFA francs) 2028: 64563000778 | 211 206 225 274 | 211 206 225 198
Activity 1.3.2.1.1 | Carry out drainage network development works in twelve (12) regional capital cities | Drainage works completed | Linear length of works completed (km) | Activity reports | DGUVT/MUAFH | Local authorities | 65,16 | 191,90 | 181,41 | 0 | 0 | 438,47 | 32 852 835 000 | 75 768 919 000 | 57 806 038 000 | 0 | 0
Activity 1.3.2.1.2 | Prepare complete technical and environmental studies for the development of drainage and road networks in twelve (12) regional capital cities | 12 Validated Detailed Design Study Reports | Number of APD reports validated | Activity reports | DGUVT/MUAFH | Local authorities | 6 | 0 | 6 | 0 | 0 | 12 | 2 646 217 805 | 0 | 2 889 805 929 | 0 | 0
Activity 1.3.2.1.3 | Carry out studies and structural works | 6 structural work study deliverables available | Number of deliverables available | Activity reports | DGUVT/MUAFH | Local authorities | Financial Programming (Thousands of CFA francs) 2024: 6; Financial Programming (Thousands of CFA francs) 2025: 2 646 217 805; Financial Programming (Thousands of CFA francs) 2026: 46 553 098 633; Financial Programming (Thousands of CFA francs) 2027: 97 443 907 982; Financial Programming (Thousands of CFA francs) 2028: 64 563 000 778 | 211 206 225 198 | 211 206 225 198
Activity 1.3.2.1.4 | Carry out the development of 24 urban parks in twelve (12) regional capital cities | Completed Urban Parks | Number of Urban Parks completed | Activity reports | DGUVT/MUAFH | Local authorities | Financial Programming (Thousands of CFA francs) 2024: 24; Financial Programming (Thousands of CFA francs) 2026: 660 000 000 | 12 | 0
Activity 1.3.2.1.5: | Ensure the follow-up/control of the development works of 24 urban parks in twelve (12) capital cities of the region | Monitoring reports | Number of monitoring reports | Activity reports | DGUVT/MUAFH | Local authorities | Financial Programming (Thousands of CFA francs) 2024: 64; Financial Programming (Thousands of CFA francs) 2026: 65000000 | 64 | 0
Expected Outcome 1.3.3: The capacity of the health sector to adapt to climate change for better protection of the population is strengthened
AXIS 2: RESEARCH AND DEVELOPMENT IN ADAPTATION TO CC
Strategic Objective 2.1: Develop innovative techniques and technologies for adaptation in CC
Expected Outcome 2.1.1: Technical and technological research in the agro-sylvo-pastoral and hydrological fields in the field of adaptation to CCs is developed | [16 empty] | 1 166 000 | 0 | 1 166 000 | 0
Action 2.1.1.1: Development of varieties adapted to the adverse effects of CCs | [16 empty] | 1 166 000 | 0 | 1 166 000 | 0
Activity 2.1.1.1.1 | Update/revision of the strategy for the management of climate-smart genetic resources | The revision of the strategy for the management of climate-smart genetic resources is updated | Number of documents in the revised Genetic Resources Management Strategy | Commerce; | CMAP; DGPA; DGPV; DGFOMER | PRECEL |  | X |  |  |  | 29 000 | 0 | 0 | 0 | 0 | 29 000 |  | 29 000 | 0
Activity 2.1.1.1.2 | . MARAH Capacity Building on Climate-Smart Livestock Legislation and Policies | MARAH's capacity on climate-smart livestock legislation and policies is strengthened | Number of documents on climate-smart livestock legislation and policies strengthened | Commerce | DGPA; DGPV; DGFOMER | PRECEL | X | X | X | X | X | 350 000 | 350 000 | 350 000 | 87 000 | 0 | 1 137 000 |  | 1 137 000 | 0
Activity 2.1.1.1.2 | Financing the activities of research centres (CNRST/INERA) on the main crops with a view to creating varieties adapted to climate risks | A financial partnership is created between the CNRST and MARAH to support varietal research | A partnership agreement is signed | Activity report (CNRST/INERA) and (MARAH)
Activity 2.1.1.1.3 | Popularize the results of research into new adapted varieties in attached and decentralised services | The results of the research are disseminated in the decentralised services of MARAH | The attached and decentralised services are informed and they are appropriate of the technical sheets of its improved seeds | Activity report (CNRST/INERA) and (MARAH)
Activity 2.1.1.1.4 | Strengthen the technical capacities of agricultural agents on the technical itineraries of new and improved seed varieties | The technical managers of the extension services are trained for the dissemination of its varieties to producers | Each technical officer in the provincial directorates is trained | MARAH Activity Report
Action 2.1.1.2: | Dissemination of research results to farms | The results of the research are disseminated to smallholder farms | Farms are aware of the existence of improved varieties that are resistant to climate risks | Activity report (CNRST/INERA) and (MARAH)
Activity 2.1.1.2.1 | Train growers in the use of new seed varieties | Producers in areas vulnerable to climate risks are trained in the use of improved varieties | Many producers are trained in the use of new seed varieties | MARAH Activity Report
Activity 2.1.1.2.2 | Equipping farmers with improved seeds that are highly productive and resilient to climate risks | Improved seeds are available to producers | Growers use its seed of improved varieties on their farms | MARAH Activity Report
Activity 2.1.1.2.3 | Promoting agricultural insurance through subsidies | Agricultural insurance is adopted by the majority of producers in high-risk areas | More than half of the producers in high-risk areas are insured | MARAH Activity Report
Action 2.1.1.3: | Promotion of new breeds of animals adapted to climate risks | New breeds of animals that are resistant to climate risks are being created | Several breeds of animals resistant to water stress and food deficit exist | Activity report (CNRST/INERA), (MARAH) and (CIRDES)
Activity 2.1.1.3.1 | Growth of animal species that are tolerant and hardy to water deficit | Animal species that are tolerant and hardy to water deficit are available | Animal species that are tolerant and hardy to water deficit are known | Activity report (CNRST/INERA) and (CIRDES)
Activity 2.1.1.3.2 | Selection and Dissemination of Genetic Progress Carriers | Broodstock carrying genetic progress are conceived | The progenitors who carry genetic progress are known to the technical services and pastoralists | Activity report (CNRST/INERA), (MARAH) and (CIRDES)
Activity 2.1.1.3.3 | Extension of animal species adapted and tolerant to water stress and food deficit with producers | Animal species adapted and tolerant to water stress and food deficit are popularized | Animal species that are adapted and tolerant to water stress and feed deficit are adopted by producers | Activity report (CNRST/INERA), (MARAH) and (CIRDES)
Action 2.1.2.4: | Promotion of new varieties of fodder species adapted to climate risks | Seeds of fodder species adapted to climate risks are created | Seeds of fodder species adapted to climate risks are available | Activity report (CNRST/INERA), (MARAH) and (CIRDES)
Activity 2.1.2.4.1 | Selection and adoption of forage species that are tolerant and hardy to water deficits and flooding | Forage species adapted to the water deficit are adopted by agro-ecological zone | Forage species adapted to the water deficit are adopted by agro-ecological zone | Activity report (CNRST/INERA), (MARAH) and (CIRDES)
Activity 2.1.2.4.2 | Extension of forage species adapted to water stress in technical services | Fodder species adapted to the water deficit are popularized by the agents of the Ministry of Livestock by agro-ecological zone | Forage species adapted to the water deficit by agro-ecological zone are used by pastoralists | MARAH Activity Report
Activity 2.1.2.4.3 | Subsidy for fodder species adapted to climate risks | Climate-resistant forage species are adopted |  | MARAH Activity Report
Activity 2.1.2.4.4 | Extension of forage species with high nutritional quality | Forage species with high nutritional quality are adopted by producers |  | Activity report (CNRST/INERA), (MARAH) and (CIRDES)
Activity 2.1.2.4.5 | Improved forage techniques and management and storage | Forage management and conservation techniques are well known |  | Activity report (CNRST/INERA), (MARAH) and (CIRDES)
Action 2.1.1.2: Development of knowledge, local know-how and endogenous best practices related to climate change resilience | [16 empty] | 0 | 0 | 0 | 0
Activity 2.1.1.2.1 | Promotion of local knowledge and know-how of agricultural practices in relation to the choice of agricultural varieties, soil fertility management | Local knowledge and know-how of good agricultural practices resilient to CC are integrated | Local knowledge and know-how are adopted by producers | Report on the activities of the technical services in connection with the Agro-pastoral sector
Activity 2.1.1.2.2 | Dissemination of best resilience practices and local knowledge and know-how by MARAH and MESRSI extension agents | The best practices of resilience and local knowledge and know-how by the extension agents of MARAH and MESRSI are popularized to agro-pastoralists | The best practices of resilience and local knowledge and know-how are adopted by producers and pastoralists | Report on the activities of the technical services in connection with the Agro-pastoral sector and the MESRSI
Action 2.1.1.2: Development of knowledge, local know-how and endogenous best practices related to climate change resilience | [16 empty] | 0 | 0 | 0 | 0
Action 2.1.1.3: Improved knowledge of water resources | [16 empty] | 0 | 0 | 0 | 0
Expected outcome 2.1.2: Technical and technological research in the fields of health, housing and energy infrastructure in the field of adaptation to CCs is developed
Action 2.1.2.1: Development of building materials and models for the realization of habitats resilient to CC
Activity 2.1.2.1.1 | Use cut laterite bricks
Activity 2.1.2.1.2 | Use recycled material
Activity 2.1.2.1.3 | Strengthen the partnership with the actors of the alert system and create the fire alarm system to react more effectively to fires in social and collective infrastructures occurring during high temperatures
Activity 2.1.2.1.4 | Strengthen people's knowledge of the impacts of climate change on the infrastructure and housing sector
Action 2.1.2.2: Development of technologies in the field of CC-friendly energies | [16 empty] | 0 | 0 | 0 | 0
Action 2.1.2.3: Strengthening health research on adaptation in CC | [16 empty] | 0 | 0 | 0 | 0
Strategic Objective 2.2: Enhance the uptake of innovative adaptation techniques and technologies in CC
Expected Outcome 2.2.1: Dissemination of scientific research and innovation results is increased
Action 2.2.1.1: Promote the use of innovative models for the construction of habitats | [17 empty] | 0 | 0 | 0
Activity 2.2.1.1.1 | Use the standard plans adapted to the terrain
Activity 2.2.1.1.2 | Use cut laterite bricks
Activity 2.2.1.1.3 | Use recycled material
Action 2.2.1.2: Promote the use of environmentally friendly materials in the construction of infrastructure | [17 empty] | 0 | 0 | 0
Activity 2.2.1.2.1 | Plant shade species that promote the fixation of the pavement
AXIS 3: GOVERNANCE OF CCS ADAPTATION INTERVENTIONS
Strategic Objective 3.1: Strengthen the policy, legal, institutional and organizational framework
Expected Outcome 3.1.1: The policy and legal framework is strengthened | [16 empty] | 445 000 |  | 22 000 | 423 000
Action 3.1.1.1: Strengthening the policy framework | [6 empty] | Financial Programming (Thousands of CFA francs) 2024: 145000; Financial Programming (Thousands of CFA francs) 2025: 95000; Financial Programming (Thousands of CFA francs) 2026: 105000 | 345 000 | 0 | 22 000 | 323 000
Activity 3.1.1.1.1 | Revise the National Sustainable Development Policy | Updated National Sustainable Development Policy available | Availability of the National Sustainable Development Policy | SP-CNDD Activity Report | SP/CNDD | Ministries of the Rural Sector, Ministry of the Economy, CRA, CPF, SPONG, Local Authorities | Physical Programming 2024: x; Physical Programming 2025: x; Financial Programming (Thousands of CFA francs) 2024: 25000; Financial Programming (Thousands of CFA francs) 2025: 25000 | 50 000 |  |  | 50 000
Activity 3.1.1.1.2 | Adopting BURKINA FASO's 2050 vision of low-carbon and climate-resilient development | BURKINA FASO's Low Carbon and Climate Resilient Development Vision 2050 adopted | Availability of BURKINA FASO's 2050 vision for low-carbon and climate-resilient development | SP-CNDD Activity Report | SP/CNDD | Ministries of the Rural Sector, Ministry of the Economy, CRA, CPF, SPONG, Local Authorities | Physical Programming 2024: x; Financial Programming (Thousands of CFA francs) 2024: 50 000 | 50 000 |  |  | 50 000
Activity 3.1.1.1.3 | Support the integration of E/SD into sectoral frameworks and local development plans | Thirty-five (35) sector-specific and LDP frameworks integrate E/SD themes | Number of revised LDPs addressing E/SD themes | SP-CNDD Activity Report | SP/CNDD | MEFP, MATDS, Local Authority | 10 | 10 | 15 |  |  | 50 000 | 50 000 | 75 000 |  |  | 175 000 |  | 12000 | 163 000
Activity 3.1.1.1.4 | Organize workshops to disseminate the guide on the consideration of E/SD themes in development frameworks | Workshops to disseminate the guide on taking into account E/SD themes in development frameworks are organized | Number of dissemination workshops held | Activity Report MEEA/SP-CNDD | MEEA/SP-CNDD | Luxdev | 10 | 10 | 15 |  |  | 20 000 | 20 000 | 30 000 |  |  | 70 000 |  | 10000 | 60 000
Activity 3.1.1.1.5 | Assessing the NDC | Adopted NDC Assessment Report | Availability of the CND evaluation report | SP-CNDD Activity Report | SP/CNDD | Other Ministries,CRA, CPF, SPONG,Local Authorities | [13 empty] | 0 | bar: Physical Programming 2025
Activity 3.1.1.1.6 | Revising the NDC | Revised CDN available | Availability of the revised NDT | SP-CNDD Activity Report | SP/CNDD | Other Ministries,CRA, CPF, SPONG,Local Authorities | [13 empty] | 0 | bar: Physical Programming 2026
Action 3.1.1.2: Strengthening the legal framework | [16 empty] | 100 000 | 0 | 0 | 100 000
Activity 3.1.1.2.1 | Drafting and adopting the Climate Change Act and related legislation | The Climate Change Act and related legislation developed | Availability of the Climate Change Act | SP-CNDD Activity Report | SP/CNDD | Other Ministries,CRA, CPF, SPONG,Local Authorities | Physical Programming 2024: x; Physical Programming 2025: x; Financial Programming (Thousands of CFA francs) 2024: 25000; Financial Programming (Thousands of CFA francs) 2025: 25000 | 50 000 |  |  | 50 000
Activity 3.1.1.2.2 | Disseminating the Climate Change Act and related legislation | Climate Change Act and Related Legislation Circulated | Number of copies distributed; Number of dissemination workshops organized | SP-CNDD Activity Report | SP/CNDD | Other Ministries,CRA, CPF, SPONG,Local Authorities | bar: Physical Programming 2025 to Physical Programming 2026
Activity 3.1.1.2.3 | Reviewing the LODD | LODD broadcast | Availability of the LODD | SP-CNDD Activity Report | SP/CNDD | Other Ministries,CRA, CPF, SPONG,Local Authorities | Physical Programming 2025: x; Financial Programming (Thousands of CFA francs) 2025: 25000; Financial Programming (Thousands of CFA francs) 2026: 25000 | 50 000 |  |  | 50 000
Activity 3.1.1.2.4 | Spreading the LODD | Revised LODD | Number of copies distributed; Number of dissemination workshops organized | SP-CNDD Activity Report | SP/CNDD | Other Ministries,CRA, CPF, SPONG,Local Authorities | bar: Physical Programming 2025 to Physical Programming 2026
Action 3.1.1.2: Strengthening the legal framework | [16 empty] | 0 | 0 | 0 | 0
Activity 3.1.1.2.2 | Drafting texts on energy efficiency in buildings | bar: Physical Programming 2024 to Financial Programming (Thousands of CFA francs) 2024
Activity 3.1.1.2.1 | Drafting texts (laws, decrees) | [15 empty] | 0 |  |  | 0
Activity 3.1.1.2.2 | Disseminate legal texts | [15 empty] | 0 |  |  | 0
Expected Outcome 3.1.2: The institutional and organizational framework is strengthened | [16 empty] | 245 000 |  | 24 000 | 221 000
Action 3.1.2.1: Strengthening the institutional framework | [16 empty] | 110 000 |  | 16 000 | 94 000
Activity 3.1.2.1.1 | Implement Burkina Faso's National Measurement, Reporting and Verification System (MRV/BF) | MRV Implementation Order Adopted | Availability of the Implementing Order | Activity Report MEEA/SP-CNDD | MEEA/SP/CNDD | SP/REDD+, SPONG, DAJC | [10 empty] | 0 |  |  | 0 | bar: Physical Programming 2024
Activity 3.1.2.1.2 | Setting up the National Climate Change Committee | The NCACC is set up | Availability of the Implementing Order | Activity Report MEEA/SP-CNDD | MEEA/SP/CNDD | SP/REDD+, SPONG, DAJC | Physical Programming 2024: 1; Financial Programming (Thousands of CFA francs) 2024: 5000 | 5 000 |  | 5000 | 0
Activity 3.1.2.1.3 | Train local stakeholders on how to take into account E/SD issues in local planning | Stakeholders are trained on the environment, sustainable development and climate change in planning | Number of actors trained | Activity Report MEEA/SP-CNDD | MEEA/SP-CNDD | ENABEL, local authority | 100 | 100 | 100 |  |  | 15000 | 15000 | 15000 |  |  | 45 000 |  | 11000 | 34 000
Activity 3.1.2.1.4 | Train budget program managers and their planners on the integration of CCs into budgeting | Budget program managers and their planners are trained | Number of people trained | SP-CNDD Activity Report | MEEA/SP-CNDD | Luxdev | 100 | 100 | 100 |  |  | 20000 | 20000 | 20000 |  |  | 60 000 |  |  | 60 000
Action 3.1.2.2: Strengthening the organizational framework | [16 empty] | 135 000 | 0 | 8 000 | 127 000
Activity 3.1.2.2.1 | Hold sessions of the Single Consultation Framework of Conventions (CCUC) | Sessions of the CCUC are held | Number of CCUC sessions held | Session Report | SP/CNDD | SP/REDD+ | 1 | 1 | 1 |  |  | 7000 | 7000 | 7000 |  |  | 21 000 |  | 4 000 | 17 000
Activity 3.1.2.2.2 | Hold sessions of the National Climate Change Committee | Sessions of the NCACC are held | Number of CONADD sessions held | Session Report | SP/CNDD | SP/REDD+ | Physical Programming 2024: 1; Physical Programming 2025: 1; Financial Programming (Thousands of CFA francs) 2024: 7000; Financial Programming (Thousands of CFA francs) 2025: 7000 | 14 000 |  | 4 000 | 10 000
Activity 3.1.2.2.3 | Holding CONADD sessions | CONADD sessions are held | Number of NCACC sessions held | Session Report | SP/CNDD | SP/REDD+ | Physical Programming 2024: 1; Physical Programming 2026: 1; Financial Programming (Thousands of CFA francs) 2024: 50000; Financial Programming (Thousands of CFA francs) 2026: 50000 | 100 000 |  |  | 100 000
Activity 3.1.2.2.4 | Increase monitoring and control of infrastructure and housing constructions
Activity 3.1.2.2.5 | Require climate change criteria (adaptation/mitigation) in architectural and urban planning competitions
Activity 3.1.2.2.6 | take into account climate change concepts in technical requirements for competitive bidding; | [16 empty] | 0
Strategic Objective 3.2: Strengthen monitoring and evaluation mechanisms and mobilization of financial resources
Expected Outcome 3.2.1: Financial resource mobilization is improved | [16 empty] | 60 000 |  | 20 000 | 40 000
Action 3.2.1.1: Strengthening the technical capacities of actors in the mobilization of financial resources | [6 empty] | Financial Programming (Thousands of CFA francs) 2024: 25000; Financial Programming (Thousands of CFA francs) 2025: 25000 | 50 000 |  | 15 000 | 35 000
Activity 3.2.1.1.1 | Train MEEA managers and partners in project development and resource mobilization techniques | MEEA staff are trained in project development and resource mobilization techniques | Number of managers trained | Activity report | SP-CNDD/MEEA | Luxdev, SP/REDD+ | Physical Programming 2024: 20; Physical Programming 2025: 20; Financial Programming (Thousands of CFA francs) 2024: 20000; Financial Programming (Thousands of CFA francs) 2025: 20000 | 40 000 |  | 5 000 | 35 000
Activity 3.2.1.1.2 | Organize training sessions for the mobilization and management of climate finance | Organized training sessions | Number of training sessions | Activity report | SP/REDD+/MEEA | SP-CNDD | Physical Programming 2024: 1; Physical Programming 2025: 1; Financial Programming (Thousands of CFA francs) 2024: 5000; Financial Programming (Thousands of CFA francs) 2025: 5000 | 10 000 |  | 10 000 | 0
Action 3.2.1.2: Development of tools for mobilizing financial resources | [16 empty] | 10 000 | 0 | 5 000 | 5 000
Activity 3.2.1.2.1 | Develop concept notes for E/SD projects | E/SD project concept notes are developed | Number of E/SD concept notes developed | Activity report | SP-CNDD/MEEA | GCF, SP-REDD+ | Physical Programming 2024: 2; Physical Programming 2025: 2; Financial Programming (Thousands of CFA francs) 2024: 5000; Financial Programming (Thousands of CFA francs) 2025: 5000 | 10 000 | 0 | 5 000 | 5 000
Activity 3.2.1.2.2 | Establish the Technical Review Committee for GEF/GCF Projects | The committee is set up | Number of Committees | Implementation Order | SP-CNDD/MEEA | GCF, DAJC | Physical Programming 2024: x; Physical Programming 2025: x; Financial Programming (Thousands of CFA francs) 2024: 0; Financial Programming (Thousands of CFA francs) 2025: 0 | 0 |  |  | 0
Activity 3.2.1.2.3 | Supporting the accreditation of national institutions to climate funds | Entities are accredited | Number of accredited entities | Activity report | SP-CNDD/MEEA | FVC, FIE, Coris Bank | Physical Programming 2024: 2 | 0 |  |  | 0
Expected Outcome 3.2.2: The monitoring and evaluation and communication system is strengthened | [16 empty] | 30 000 |  | 5500 | 24 500
Action 3.2.2.1: Strengthening the monitoring and evaluation system | [17 empty] | #REF! | #REF! | #REF!
Action 3.2.2.2: Strengthening the communication system | [16 empty] | 30 000 | 0 | 5 500 | 24 500
Activity 3.2.2.2.1 | Strengthen the partnership with stakeholders to respond more effectively to fires in social and collective infrastructures occurring during hot weather
Activity 3.2.2.2.2 | Create a fire alarm system to respond more effectively to fires in social and collective infrastructures that occur during hot weather
Activity 3.2.2.2.3 | Strengthen people's knowledge of the impacts of climate change on the infrastructure and housing sector
Activity 3.2.2.2.4 | Train the actors in charge of the animation of the national MRV platform | Actors in charge of the animation of the national MRV platform are trained | Number of actors in charge of the animation of the national MRV platform trained | SP-CNDD Activity Report | MEEA/SP-CNDD | MARA, MEMC, MESRI, MEFP, CT | 40 | 40 | 40 |  |  | 10000 | 10000 | 10000 |  |  | 30 000 |  | 5500 | 24 500
TOTAL | [16 empty] | 211 233 879 924 | 211 206 259 898 | 24 961 500 | 2 658 080